## Capacity Plan
[7 empty] | 2025-12-01 | 2025-12-31 | 2026-01-01 | 2026-01-31 | 2026-02-01 | 2026-02-28 | 2026-03-01 | 2026-03-31 | 2026-04-01 | 2026-04-30 | 2026-05-01 | 2026-05-31 | 2026-06-01 | 2026-06-30 | 2026-07-01 | 2026-07-31 | 2026-08-01 | 2026-08-31 | 2026-09-01 | 2026-09-30 | 2026-10-01 | 2026-10-31 | 2026-11-01 | 2026-11-30 | 2026-12-01 | 2026-12-31 | 2027-01-01 | 2027-01-31
| EMEA North - CAPACITY PLAN | [5 empty] | 2025-12-01 | 23 | 2026-01-01 | 22 | 2026-02-01 | 20 | 2026-03-01 | 22 | 2026-04-01 | 22 | 2026-05-01 | 21 | 2026-06-01 | 22 | 2026-07-01 | 23 | 2026-08-01 | 21 | 2026-09-01 | 22 | 2026-10-01 | 22 | 2026-11-01 | 21 | 2026-12-01 | 23 | 2027-01-01 | 21
|  | 2026 |  |  | Bank Holidays France |  | 2025-12-31: 1; 2026-01-31: 1; 2026-02-28: 0; 2026-03-31: 0; 2026-04-30: 1; 2026-05-31: 3; 2026-06-30: 1; 2026-07-31: 1; 2026-08-31: 1; 2026-09-30: 0; 2026-10-31: 0; 2026-11-30: 1; 2026-12-31: 1; 2027-01-31: 0
[5 empty] | Bank Holidays Prague : |  | 2025-12-31: 2; 2026-01-31: 1; 2026-02-28: 0; 2026-03-31: 0; 2026-04-30: 2; 2026-05-31: 2; 2026-06-30: 0; 2026-07-31: 0; 2026-08-31: 0; 2026-09-30: 0; 2026-10-31: 1; 2026-11-30: 1; 2026-12-31: 3; 2027-01-31: 1
TRI | Type | ISM | IPM | Projects / Activities | STATUS / Comm |  | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days | % | Man Days
[5 empty] | GLOBAL EMEA North AVAIBILITY (%) : |  | 2025-12-01: #REF!; 2026-01-01: #REF!; 2026-02-01: #REF!; 2026-03-01: #REF!; 2026-04-01: #REF!; 2026-05-01: #REF!; 2026-06-01: #REF!; 2026-07-01: #REF!; 2026-08-01: #REF!; 2026-09-01: #REF!; 2026-10-01: #REF!; 2026-11-01: #REF!; 2026-12-01: #REF!; 2027-01-01: #REF!
|  | X | X | X | X | X | bar: 2025-12-01 to 2027-01-31
| Project (Active) | manager_1_name | employee_1_name | project 1 | W2.2 new pilot entities live in feb 09th / W2.4 March 5th go live |  | 21.74% | 5 | 13.64% | 3 | 10% | 2 | 4.545% | 1 | 4.545% | 1 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| Project (Active) | manager_1_name | employee_1_name | project 2 | Vietnam will go live on 1st April, then 1 month hypercare |  | 17.39% | 4 | 18.18% | 4 | 15% | 3 | 9.091% | 2 | 9.091% | 2 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| Project (Active) | manager_1_name | employee_1_name | project 3 | KO on the 03/03 - probably less than 130h. First wave should be completed on May 11. Other waves would be in July / September. To be reassigned |  | 17.39% | 4 | 18.18% | 4 | 0% |  | 13.64% | 3 | 13.64% | 3 | 14.29% | 3 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| Project (Active) | manager_1_name | employee_1_name | project 4 | Jan 5th go live |  | 2025-12-01: 26.09%; 2025-12-31: 6; 2026-01-01: 13.64%; 2026-01-31: 3; 2026-02-01: 0%; 2026-03-01: 0%; 2026-04-01: 0%; 2026-05-01: 0%; 2026-06-01: 0%; 2026-07-01: 0%; 2026-08-01: 0%; 2026-09-01: 0%; 2026-10-01: 0%; 2026-11-01: 0%; 2026-12-01: 0%; 2027-01-01: 0%
| Admin | manager_1_name | employee_1_name | ** CIP Support |  |  | 2025-12-01: 2.174%; 2025-12-31: 0.5; 2026-01-01: 2.273%; 2026-01-31: 0.5; 2026-02-01: 0%; 2026-03-01: 0%; 2026-04-01: 0%; 2026-05-01: 0%; 2026-06-01: 0%; 2026-07-01: 0%; 2026-08-01: 0%; 2026-09-01: 0%; 2026-10-01: 0%; 2026-11-01: 0%; 2026-12-01: 0%; 2027-01-01: 0%
| Admin | manager_1_name | employee_1_name | ** Admin Time & Internal Initatives | 6h per Week / 3 Days Month |  | 13.04% | 3 | 13.64% | 3 | 15% | 3 | 13.64% | 3 | 13.64% | 3 | 14.29% | 3 | 13.64% | 3 | 13.04% | 3 | 14.29% | 3 | 13.64% | 3 | 13.64% | 3 | 14.29% | 3 | 13.04% | 3 | 14.29% | 3
| Admin | manager_1_name | employee_1_name | ** Training & Personal Education | 2h per week / 1 Day Month |  | 4.348% | 1 | 4.545% | 1 | 5% | 1 | 4.545% | 1 | 4.545% | 1 | 4.762% | 1 | 4.545% | 1 | 4.348% | 1 | 4.762% | 1 | 4.545% | 1 | 4.545% | 1 | 4.762% | 1 | 4.348% | 1 | 4.762% | 1
| Absences | manager_1_name | employee_1_name | ** Bank Holiday (Prague) |  |  | 8.696% | 2 | 4.545% | 1 | 0% | 0 | 0% | 0 | 9.091% | 2 | 9.524% | 2 | 0% | 0 | 4.348% | 1 | 0% | 0 | 0% | 0 | 4.545% | 1 | 4.762% | 1 | 13.04% | 3 | 4.762% | 1
| Absences | manager_1_name | employee_1_name | ** Vacations |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 47.62% | 10 | 100% | 22 | 52.17% | 12 | 4.762% | 1 | 0% |  | 45.45% | 10 | 0% |  | 0% |  | 0%
|  | manager_1_name | employee_1_name | 4 Projects |  |  | 2025-12-01: -10.87%; 2026-01-01: 11.36%; 2026-02-01: 55%; 2026-03-01: 54.55%; 2026-04-01: 45.45%; 2026-05-01: 9.524%; 2026-06-01: -18.18%; 2026-07-01: 26.09%; 2026-08-01: 76.19%; 2026-09-01: 81.82%; 2026-10-01: 31.82%; 2026-11-01: 76.19%; 2026-12-01: 69.57%; 2027-01-01: 76.19%
| Project (Active) | manager_1_name | employee_2_name | client 1 - project abc | UAT to be confirmed by mid week 11. Prod2Test to be done, then test entity to be configured. Then WS development (on-hold) |  | 8.696% | 2 | 13.64% | 3 | 10% | 2 | 9.091% | 2 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| Project (Active) | manager_1_name | employee_2_name | client 2 - project xyz | Completed |  | 2025-12-01: 2.174%; 2025-12-31: 0.5; 2026-01-01: 0%; 2026-02-01: 0%; 2026-03-01: 0%; 2026-04-01: 0%; 2026-05-01: 0%; 2026-06-01: 0%; 2026-07-01: 0%; 2026-08-01: 0%; 2026-09-01: 0%; 2026-10-01: 0%; 2026-11-01: 0%; 2026-12-01: 0%; 2027-01-01: 0%
| Project (Active) | manager_1_name | employee_2_name | client 3 | Kick-off week of 23/03. Then the design phase will be mainly driven by the client. |  | 2.174% | 0.5 | 0% |  | 20% | 4 | 18.18% | 4 | 18.18% | 4 | 19.05% | 4 | 18.18% | 4 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| Project (Active) | manager_1_name | employee_2_name | client 5 | Completed | x | 8.696% | 2 | 2.273% | 0.5 | 10% | 2 | 9.091% | 2 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| Project (Active) | manager_1_name | employee_2_name | client 999 | Completed |  | 2025-12-01: 2.174%; 2025-12-31: 0.5; 2026-01-01: 0%; 2026-02-01: 0%; 2026-03-01: 0%; 2026-04-01: 0%; 2026-05-01: 0%; 2026-06-01: 0%; 2026-07-01: 0%; 2026-08-01: 0%; 2026-09-01: 0%; 2026-10-01: 0%; 2026-11-01: 0%; 2026-12-01: 0%; 2027-01-01: 0%
| Project (Active) | manager_1_name | employee_2_name | client 123 | Go-live on the 23/03 |  | 2025-12-01: 2.174%; 2025-12-31: 0.5; 2026-01-01: 0.9091%; 2026-01-31: 0.2; 2026-02-01: 0%; 2026-03-01: 0%; 2026-04-01: 0%; 2026-05-01: 0%; 2026-06-01: 0%; 2026-07-01: 0%; 2026-08-01: 0%; 2026-09-01: 0%; 2026-10-01: 0%; 2026-11-01: 0%; 2026-12-01: 0%; 2027-01-01: 0%
| Project (Active) | manager_1_name | employee_2_name | client abc | Completed |  | 2025-12-01: 4.348%; 2025-12-31: 1; 2026-01-01: 2.273%; 2026-01-31: 0.5; 2026-02-01: 0%; 2026-03-01: 0%; 2026-04-01: 0%; 2026-05-01: 0%; 2026-06-01: 0%; 2026-07-01: 0%; 2026-08-01: 0%; 2026-09-01: 0%; 2026-10-01: 0%; 2026-11-01: 0%; 2026-12-01: 0%; 2027-01-01: 0%
o | Project (Active) | manager_1_name | employee_2_name | super important VIP client | Completed |  | 2025-12-01: 0%; 2026-01-01: 1.364%; 2026-01-31: 0.3; 2026-02-01: 0%; 2026-03-01: 0%; 2026-04-01: 0%; 2026-05-01: 0%; 2026-06-01: 0%; 2026-07-01: 0%; 2026-08-01: 0%; 2026-09-01: 0%; 2026-10-01: 0%; 2026-11-01: 0%; 2026-12-01: 0%; 2027-01-01: 0%
o | Project (Active) | manager_1_name | employee_2_name | blah blah blah | Setting up the microservices in the new entity, to be finished by 21/03 |  | 0% |  | 0% |  | 7.5% | 1.5 | 18.18% | 4 | 18.18% | 4 | 19.05% | 4 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| E&C | manager_1_name | employee_2_name | consulting engagement ongoing | Daily cases, Site review 2024 |  | 21.74% | 5 | 22.73% | 5 | 25% | 5 | 18.18% | 4 | 18.18% | 4 | 19.05% | 4 | 18.18% | 4 | 17.39% | 4 | 19.05% | 4 | 18.18% | 4 | 18.18% | 4 | 19.05% | 4 | 17.39% | 4 | 19.05% | 4
| Admin | manager_1_name | employee_2_name | ** CIP Support |  |  | 2.174% | 0.5 | 2.273% | 0.5 | 2.5% | 0.5 | 2.273% | 0.5 | 2.273% | 0.5 | 2.381% | 0.5 | 2.273% | 0.5 | 2.174% | 0.5 | 2.381% | 0.5 | 2.273% | 0.5 | 2.273% | 0.5 | 2.381% | 0.5 | 2.174% | 0.5 | 2.381% | 0.5
| Admin | manager_1_name | employee_2_name | ** Admin Time & Internal Initatives | 6h per Week / 3 Days Month |  | 13.04% | 3 | 13.64% | 3 | 15% | 3 | 13.64% | 3 | 13.64% | 3 | 14.29% | 3 | 13.64% | 3 | 13.04% | 3 | 14.29% | 3 | 13.64% | 3 | 13.64% | 3 | 14.29% | 3 | 13.04% | 3 | 14.29% | 3
| Admin | manager_1_name | employee_2_name | ** Training & Personal Education | 2h per week / 1 Day Month |  | 4.348% | 1 | 4.545% | 1 | 5% | 1 | 4.545% | 1 | 4.545% | 1 | 4.762% | 1 | 4.545% | 1 | 4.348% | 1 | 4.762% | 1 | 4.545% | 1 | 4.545% | 1 | 4.762% | 1 | 4.348% | 1 | 4.762% | 1
| Admin | manager_1_name | employee_2_name | ** Bank Holiday (Prague) |  |  | 8.696% | 2 | 4.545% | 1 | 0% | 0 | 0% | 0 | 9.091% | 2 | 9.524% | 2 | 0% | 0 | 4.348% | 1 | 0% | 0 | 0% | 0 | 4.545% | 1 | 4.762% | 1 | 13.04% | 3 | 4.762% | 1
| Absences | manager_1_name | employee_2_name | ** Vacations |  |  | 0% |  | 0% |  | 0% |  | 4.545% | 1 | 9.091% | 2 | 4.762% | 1 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
|  | manager_1_name | employee_2_name | 10 Projects |  |  | 2025-12-01: 19.57%; 2026-01-01: 31.82%; 2026-02-01: 5%; 2026-03-01: 2.273%; 2026-04-01: 6.818%; 2026-05-01: 7.143%; 2026-06-01: 43.18%; 2026-07-01: 58.7%; 2026-08-01: 59.52%; 2026-09-01: 61.36%; 2026-10-01: 56.82%; 2026-11-01: 54.76%; 2026-12-01: 50%; 2027-01-01: 54.76%
Note on O32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: tbc
Note on Q32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: tbc